## 文档信息
[eOrder]
[客户名称]
文档版本信息
项目名称: |  |  |  | 项目编号
文档标题 : |  |  |  | 文档版本号:
项目经理: |  |  |  | 文档版本日期:
修订人: |  |  |  | 修订日期:
审核人: |  |  |  | 审核日期:
文档版本履历
版本号 | 修订日期 | 修订人 | 审核人 | 版本描述
V1.1 | 2014-11-27 | Annie |  | 初始化
模板版本履历（在使用前删除）
版本号 | 修订日期 | 修订人 | 审核人 | 批准人 | 变更内容
V1.0 | 2014-11-27 | Annie |  |  | 新建

## 需求跟踪矩阵
业务需求 | 用户需求 | 需求规格说明书 | 概要设计说明书 | 详细设计说明书 | 测试用例编号 | 其他
BR_01_电子菜单 | UR_001-浏览菜单 | UC_001_浏览菜单 | 5.2.1 | 4.1 | 2.1 浏览菜单
BR_02_电子水单 | UR_002-点菜 | UC_003_点菜 | 5.2.2，5.2.3 | 4.2,4.3 | 2.3 点菜下单
BR_02_电子水单 | UR_003-浏览历史订单 | UC_002_浏览历史订单 | 5.2.5 | 4.4 | 2.2 浏览会员历史订单
BR_02_电子水单 | UR_004-下订单 | UC_004_下定单 | 5.2.4 | 4.2 | 2.4 确认订单
BR_03_收银 | UR_005-消费清单
BR_03_收银 | UR_006-更新订单
BR_04_菜单/菜品维护 | UR_007-创建菜品
BR_04_菜单/菜品维护 | UR_008-更新菜品
BR_05_会员管理 | UR_009-注册和查看会员信息
BR_06_用户管理 | UR_010-用户管理 | UC_005_用户登录 | 4.2.1 | 5.1 | 2.5 登录
BR_06_用户管理 | UR_010-用户管理 | UC_006_用户管理 | 4.2.2,4.2.3 | 5.2,5.3 | 2.8 用户管理
BR_06_用户管理 | UR_010-用户管理 | UC_007_用户管理-创建用户 | 4.2.2 | 5.2 | 2.8 用户管理
BR_06_用户管理 | UR_010-用户管理 | UC_008_用户管理-更新用户 | 4.2.2.4.2.3 | 5.3 | 2.8 用户管理
BR_07_权限管理 | UR_011-权限管理 | UC_012_权限管理 | 4.2.6 | 5.5 | 2.6 权限管理
BR_07_权限管理 | UR_011-权限管理 | UC_013_权限管理-创建权限 | 4.2.6 | 5.5 | 2.6 权限管理
BR_07_权限管理 | UR_011-权限管理 | UC_014_权限管理-更新权限 | 4.2.6 | 5.5 | 2.6 权限管理
BR_07_权限管理 | UR_012-角色管理 | UC_010_角色管理 | 4.2.4,4.2.5 | 5.4, 5.6 | 2.7 角色管理
BR_07_权限管理 | UR_012-角色管理 | UC_011_角色管理-创建角色 | 4.2.4 | 5.4 | 2.7 角色管理
BR_07_权限管理 | UR_012-角色管理 | UC_012_角色管理-更新角色 | 4.2.4,4.2.5 | 5.6 | 2.7 角色管理
BR_08_运营管理 | UR_013-运营管理
Note on B3: [唯一编号] 如 BR001, Br002,….
Note on E3: 概要设计里描述此需求的章节
Note on F3: 详细设计里描述此需求的章节

## 工作分解结构
模块 | 功能点 | 需求规格说明书 | 概要设计说明书 | 详细设计说明书 | 测试用例编号 | 其他
移动点菜模块 | 浏览菜单 | UC_001_浏览菜单 | 5.2.1 | 4.1 | 2.1 浏览菜单
| 点菜 | UC_003_点菜 | 5.2.2 | 4.2,4.3 | 2.3 点菜下单
| 浏览历史订单 | UC_002_浏览历史订单 | 5.2.5 | 4.4 | 2.2 浏览会员历史订单
| 下订单 | UC_004_下定单 | 5.2.4 | 4.2 | 2.4 确认订单
| 浏览编辑订单详情 | UC_003_点菜 | 5.2.3 | 4.2 | 2.3 点菜下单
后台收银模块 | 打印账单
结账
浏览流水
菜单管理模块 | 创建/编辑菜品分类
创建/编辑菜品
浏览菜单分类
浏览菜单明细
浏览菜品明细
会员管理模块 | 创建/编辑会员等级
查询用户会员信息
编辑用户会员信息
权限管理模块 | 用户登录 | UC_005_用户登录 | 4.2.1 | 5.1 | 2.5 登录
| 创建/维护用户信息 | UC_006_用户管理 | 4.2.2,4.2.3 | 5.2, 5.3 | 2.8 用户管理
|  | UC_007_用户管理-创建用户 | 4.2.2 | 5.2 | 2.8 用户管理
| 用户角色分配 | UC_008_用户管理-更新用户 | 4.2.3 | 5.3 | 2.8 用户管理
| 创建/编辑角色信息 | UC_010_角色管理 | 4.2.4,4.2.5 | 5.4,5.6 | 2.7 角色管理
|  | UC_011_角色管理-创建角色 | 4.2.4 | 5.4 | 2.7 角色管理
| 角色权限分配 | UC_012_角色管理-更新角色 | 4.2.4,4.2.5 | 5.6 | 2.7 角色管理
| 创建/编辑权限 | UC_013_权限管理-创建权限 | 4.2.6 | 5.5 | 2.6 权限管理
|  | UC_014_权限管理-更新权限 | 4.2.6 | 5.5 | 2.6 权限管理
Note on D1: 概要设计里描述此需求的章节
Note on E1: 详细设计里描述此需求的章节

## 垂直跟踪
需求(req)A
设计(Design)B |  | Req.1 | Req.2 | Req.3 | Req.4 | Req.5 | Req.6 | Req.7 | Req.8 | Req.9 | Req.10
Design 1 | bar: Req.1 to Req.2; Req.4 to Req.5; Req.7 to Req.10
Design 2 | bar: Req.2; Req.10
Design 3 | bar: Req.2; Req.5 to Req.6; Req.10
Design 4 | bar: Req.2; Req.10
Design 5 | bar: Req.4; Req.6; Req.9
Design 6 | bar: Req.8; Req.10
Design 7 | bar: Req.5
Design 8 | bar: Req.2; Req.4; Req.6 to Req.7
Design 9 | bar: Req.7 to Req.9
Design 10 | bar: Req.2; Req.5; Req.7
说明：描述某一项相关的、 在两个特定的项目阶段之间的依赖关系用垂直跟踪描述。如在“系统需求”和“系统设计”两个阶段之间等。

## 水平跟踪
需求(req) A
需求 (req)B |  | Req.1 | Req.2 | Req.3 | Req.4 | Req.5 | Req.6 | Req.7 | Req.8 | Req.9 | Req.10
Req.1 | bar: Req.2; Req.4 to Req.5; Req.7 to Req.10
Req.2 | bar: Req.10
Req.3 | bar: Req.5 to Req.6; Req.10
Req.4 | bar: Req.4; Req.10
Req.5 | bar: Req.4 to Req.6; Req.9
Req.6 | bar: Req.4 to Req.6; Req.8; Req.10
Req.7 | bar: Req.4 to Req.7
Req.8 | bar: Req.4 to Req.8
Req.9 | bar: Req.4 to Req.9
Req.10 | bar: Req.4 to Req.10
说明：描述某一项相关的、 在项目的一个特定阶段内部的依赖关系用水平跟踪来表示。如在“系统需求”或者“系统设计”阶段内部等。

## LookUp
用户定义 |  | 业务需求 |  | 用户需求 | 软件需求 | 测试用例 | 概要设计
USR_01 | 顾客 | BR_01 | 电子菜单 | UR_001-浏览菜单 | UC_001 | 2.1 浏览菜单 | 5.2.1
USR_02 | 服务员 | BR_02 | 电子水单 | UR_002-点菜 | UC_002 | 2.2 浏览会员历史订单 | 5.2.2
USR_03 | 收银员 | BR_03 | 收银 | UR_003-浏览历史订单 | UC_003 | 2.3 点菜下单 | 5.2.3
USR_04 | 菜品管理员 | BR_04 | 菜单/菜品维护 | UR_004-下订单 | UC_004 | 2.4 确认订单 | 5.2.4
USR_05 | 系统管理员 | BR_05 | 会员管理 | UR_005-消费清单 | UC_005 | 2.5 登录 | 5.2.5
|  | BR_06 | 用户管理 | UR_006-更新订单 | UC_006 | 2.6 权限管理 | 4.2.1
|  | BR_07 | 权限管理 | UR_007-创建菜品 | UC_007 | 2.7 角色管理 | 4.2.2
|  | BR_08 | 运营管理 | UR_008-更新菜品 | UC_008 | 2.8 用户管理 | 4.2.3
|  |  |  | UR_009-注册和查看会员信息 | UC_009 |  | 4.2.4
|  |  |  | UR_010-用户管理 | UC_010 |  | 4.2.5
|  |  |  | UR_011-权限管理 | UC_011 |  | 4.2.6
|  |  |  | UR_012-角色管理 | UC_012
|  |  |  | UR_013-运营管理 | UC_013
UC_014
UC_015
UC_016
UC_017
UC_018
UC_019
UC_020